## Question 1
Important 1. Only reducing activity duration on the critical path (CP) will reduce project time overall (= do NOT crash any activity while it is NOT on the CP) 2. Do the crashing SLOW = 1 time period overall project duration reduction at a time (= if you have parallel CPs, this means reducing several activities each by 1 time period) 3. Reduce each time period of overall project duration always at the lowest possible cost; i.e. crash the activity(s) on the CP with the lowest crash cost (= if you have parallel CPs, this means adding the individual crash costs together) 4. Each activity has a limit as to how much it can be crashed (= keep track for each activity on how many crash time periods you have already used up) Notice: after EACH 1 time period overall project duration reduction you MUST re-assess where the CP runs now because this will change if you have a project with parallel network paths.
| Base Plan | [16 empty] | Indirect Cost is $1500 with $50 reduction for one time unit shorten | [6 empty] | Iteration Cycle | Project duration | Crashed activities | Crash cost | direct cost | Indirect cost | Total cost
[5 empty] | 3 |  | 7 | 7 |  | 10 | 10 |  | 12 |  |  |  | What can be crashed on Base plan: The activity we can crash here is B, D,H and I. The cost of crashing D is the least. | Activity ID | Slope ($) | Max crash time | Direct Cost
[5 empty] | 0 | B |  | 3 | F |  | 3 | G | [8 empty] | Normal |  | Crash |  | Base | 17 | - | - | 2000 | 1500 | 3500
[5 empty] | 3 | 4 | 7 | 10 | 3 | 13 | 13 | 2 | 15 | [7 empty] | Time | Cost | Time | Cost | 1 | 16 | D | 40 | 2040 | 1450 | 3490
[14 empty] | 15 |  | 17 |  | A | 0 | 0 | 3 | 150 | 3 | 150 | 2 | 15 | H | 60 | 2100 | 1400 | 3500
|  | 0 |  | 3 |  |  |  | 7 |  | 11 |  |  |  | 0 | I |  |  | B | 100 | 1 | 4 | 200 | 3 | 300 | 3 | 14 | H | 60 | 2160 | 1350 | 3510
|  | 0 | A |  |  |  |  | 0 | D |  |  |  |  | 15 | 2 | 17 |  | C | 60 | 1 | 3 | 250 | 2 | 310 | 4 | 13 | B | 100 | 2260 | 1300 | 3560
|  | 0 | 3X | 3 |  |  |  | 7 | 4 | 11 | [7 empty] | D | 40 | 1 | 4 | 200 | 3 | 240 | 5 | 12 | I | 200 | 2460 | 1250 | 3710
[18 empty] | E | 0 | 0 | 2 | 250 | 2 | 250
[5 empty] | 3 |  | 6 | 6 |  | 8 | 11 |  | 15 |  |  |  |  | F | 30 | 2 | 3 | 200 | 1 | 260
[5 empty] | 1 | C |  | 3 | E |  | 0 | H | [5 empty] | G | 20 | 1 | 2 | 250 | 1 | 270
[5 empty] | 4 | 3 | 7 | 9 | 2X | 11 | 11 | 4 | 15 |  |  |  |  | H | 60 | 2 | 4 | 300 | 2 | 420
[18 empty] | I | 200 | 1 | 2 | 200 | 1 | 400
| Iteration 1 | [16 empty] | Indirect Cost is $1500 with $50 reduction for one time unit shorten
[5 empty] | 3 |  | 7 | 7 |  | 10 | 10 |  | 12 |  |  |  | What can be crashed on iteration 1: The activity we can crash here is B, H and I. The cost of crashing H is the least. | Activity ID | Slope ($) | Max crash time | Direct Cost
[5 empty] | 0 | B |  | 2 | F |  | 2 | G | [8 empty] | Normal |  | Crash
[5 empty] | 3 | 4 | 7 | 9 | 3 | 12 | 12 | 2 | 14 | [7 empty] | Time | Cost | Time | Cost
[14 empty] | 14 |  | 16 |  | A | 0 | 0 | 3 | 150 | 3 | 150
|  | 0 |  | 3 |  |  |  | 7 |  | 10 |  |  |  | 0 | I |  |  | B | 100 | 1 | 4 | 200 | 3 | 300
|  | 0 | A |  |  |  |  | 0 | D |  |  |  |  | 14 | 2 | 16 |  | C | 60 | 1 | 3 | 250 | 2 | 310
|  | 0 | 3X | 3 |  |  |  | 7 | 3X | 10 | [7 empty] | D | - | 0 | 4 | 200 | 3 | 240
[18 empty] | E | 0 | 0 | 2 | 250 | 2 | 250
[5 empty] | 3 |  | 6 | 6 |  | 8 | 10 |  | 14 |  |  |  |  | F | 30 | 2 | 3 | 200 | 1 | 260
[5 empty] | 1 | C |  | 2 | E |  | 0 | H | [5 empty] | G | 20 | 1 | 2 | 250 | 1 | 270
[5 empty] | 4 | 3 | 7 | 8 | 2X | 10 | 10 | 4 | 14 |  |  |  |  | H | 60 | 2 | 4 | 300 | 2 | 420
[18 empty] | I | 200 | 1 | 2 | 200 | 1 | 400
| Iteration 2 | [16 empty] | Indirect Cost is $1500 with $50 reduction for one time unit shorten
[5 empty] | 3 |  | 7 | 7 |  | 10 | 10 |  | 12 |  |  |  | What can be crashed on iteration 2: The activity we can crash here is B, H and I. The cost of crashing H is the least. | Activity ID | Slope ($) | Max crash time | Direct Cost
[5 empty] | 0 | B |  | 1 | F |  | 1 | G | [8 empty] | Normal |  | Crash
[5 empty] | 3 | 4 | 7 | 8 | 3 | 11 | 11 | 2 | 13 | [7 empty] | Time | Cost | Time | Cost
[14 empty] | 13 |  | 15 |  | A | 0 | 0 | 3 | 150 | 3 | 150
|  | 0 |  | 3 |  |  |  | 7 |  | 10 |  |  |  | 0 | I |  |  | B | 100 | 1 | 4 | 200 | 3 | 300
|  | 0 | A |  |  |  |  | 0 | D |  |  |  |  | 13 | 2 | 15 |  | C | 60 | 1 | 3 | 250 | 2 | 310
|  | 0 | 3X | 3 |  |  |  | 7 | 3X | 10 | [7 empty] | D | - | 0 | 4 | 200 | 3 | 240
[18 empty] | E | 0 | 0 | 2 | 250 | 2 | 250
[5 empty] | 3 |  | 6 | 6 |  | 8 | 10 |  | 13 |  |  |  |  | F | 30 | 2 | 3 | 200 | 1 | 260
[5 empty] | 1 | C |  | 2 | E |  | 0 | H | [5 empty] | G | 20 | 1 | 2 | 250 | 1 | 270
[5 empty] | 4 | 3 | 7 | 8 | 2X | 10 | 10 | 3 | 13 |  |  |  |  | H | 60 | 1 | 4 | 300 | 2 | 420
[18 empty] | I | 200 | 1 | 2 | 200 | 1 | 400
| Iteration 3 | [16 empty] | Indirect Cost is $1500 with $50 reduction for one time unit shorten
[5 empty] | 3 |  | 7 | 7 |  | 10 | 10 |  | 12 |  |  |  | What can be crashed on iteration 3: Two critical path here, Activity F&G and D&H are paralleled. If we want to shorten the duration for the whole project, we need to crash activities on both paths together (eg, F&D, F&H,G&D, G&H), but from the diagram, we know D&H can not be crashed any more. Therefore, at this stage, the activity we can crash is B and I. The cost of crashing B is the least. | Activity ID | Slope ($) | Max crash time | Direct Cost
[5 empty] | 0 | B |  | 0 | F |  | 0 | G | [8 empty] | Normal |  | Crash
[5 empty] | 3 | 4 | 7 | 7 | 3 | 10 | 10 | 2 | 12 | [7 empty] | Time | Cost | Time | Cost
[14 empty] | 12 |  | 14 |  | A | 0 | 0 | 3 | 150 | 3 | 150
|  | 0 |  | 3 |  |  |  | 7 |  | 10 |  |  |  | 0 | I |  |  | B | 100 | 1 | 4 | 200 | 3 | 300
|  | 0 | A |  |  |  |  | 0 | D |  |  |  |  | 12 | 2 | 14 |  | C | 60 | 1 | 3 | 250 | 2 | 310
|  | 0 | 3X | 3 |  |  |  | 7 | 3X | 10 | [7 empty] | D | - | 0 | 4 | 200 | 3 | 240
[18 empty] | E | 0 | 0 | 2 | 250 | 2 | 250
[5 empty] | 3 |  | 6 | 6 |  | 8 | 10 |  | 12 |  |  |  |  | F | 30 | 2 | 3 | 200 | 1 | 260
[5 empty] | 1 | C |  | 2 | E |  | 0 | H | [5 empty] | G | 20 | 1 | 2 | 250 | 1 | 270
[5 empty] | 4 | 3 | 7 | 8 | 2X | 10 | 10 | 2X | 12 |  |  |  |  | H | - | 0 | 4 | 300 | 2 | 420
[18 empty] | I | 200 | 1 | 2 | 200 | 1 | 400
| Iteration 4 | [16 empty] | Indirect Cost is $1500 with $50 reduction for one time unit shorten
[5 empty] | 3 |  | 6 | 6 |  | 9 | 9 |  | 11 |  |  |  | What can be crashed on iteration 4: The only activity we can crash here is I. | Activity ID | Slope ($) | Max crash time | Direct Cost
[5 empty] | 0 | B |  | 0 | F |  | 0 | G | [8 empty] | Normal |  | Crash
[5 empty] | 3 | 3X | 6 | 6 | 3 | 9 | 9 | 2 | 11 | [7 empty] | Time | Cost | Time | Cost
[14 empty] | 11 |  | 13 |  | A | 0 | 0 | 3 | 150 | 3 | 150
|  | 0 |  | 3 |  |  |  | 6 |  | 9 |  |  |  | 0 | I |  |  | B | - | 0 | 4 | 200 | 3 | 300
|  | 0 | A |  |  |  |  | 0 | D |  |  |  |  | 11 | 2 | 13 |  | C | 60 | 1 | 3 | 250 | 2 | 310
|  | 0 | 3X | 3 |  |  |  | 6 | 3X | 9 | [7 empty] | D | - | 0 | 4 | 200 | 3 | 240
[18 empty] | E | 0 | 0 | 2 | 250 | 2 | 250
[5 empty] | 3 |  | 6 | 6 |  | 8 | 9 |  | 11 |  |  |  |  | F | 30 | 2 | 3 | 200 | 1 | 260
[5 empty] | 0 | C |  | 1 | E |  | 0 | H | [5 empty] | G | 20 | 1 | 2 | 250 | 1 | 270
[5 empty] | 3 | 3 | 6 | 7 | 2X | 9 | 9 | 2X | 11 |  |  |  |  | H | - | 0 | 4 | 300 | 2 | 420
[18 empty] | I | 200 | 1 | 2 | 200 | 1 | 400
| Iteration 5 | [16 empty] | Indirect Cost is $1500 with $50 reduction for one time unit shorten
[5 empty] | 3 |  | 6 | 6 |  | 9 | 9 |  | 11 |  |  |  | What can be crashed on iteration 5: No activity can be crashed here to shorten the duration for the whole project. It has reached the crash point of the network. | Activity ID | Slope ($) | Max crash time | Direct Cost
[5 empty] | 0 | B |  | 0 | F |  | 0 | G | [8 empty] | Normal |  | Crash
[5 empty] | 3 | 3X | 6 | 6 | 3 | 9 | 9 | 2 | 11 | [7 empty] | Time | Cost | Time | Cost
[14 empty] | 11 |  | 12 |  | A | 0 | 0 | 3 | 150 | 3 | 150
|  | 0 |  | 3 |  |  |  | 6 |  | 9 |  |  |  | 0 | I |  |  | B | - | 0 | 4 | 200 | 3 | 300
|  | 0 | A |  |  |  |  | 0 | D |  |  |  |  | 11 | 1X | 12 |  | C | 60 | 1 | 3 | 250 | 2 | 310
|  | 0 | 3X | 3 |  |  |  | 6 | 3X | 9 | [7 empty] | D | - | 0 | 4 | 200 | 3 | 240
[18 empty] | E | 0 | 0 | 2 | 250 | 2 | 250
[5 empty] | 3 |  | 6 | 6 |  | 8 | 9 |  | 11 |  |  |  |  | F | 30 | 2 | 3 | 200 | 1 | 260
[5 empty] | 0 | C |  | 1 | E |  | 0 | H | [5 empty] | G | 20 | 1 | 2 | 250 | 1 | 270
[5 empty] | 3 | 3 | 6 | 7 | 2X | 9 | 9 | 2X | 11 |  |  |  |  | H | - | 0 | 4 | 300 | 2 | 420
[18 empty] | I | - | 0 | 2 | 200 | 1 | 400

## Question 2
Project duration | Crashed activities | Crash cost | Direct cost | Indirect cost | Total cost | ABFGI | ACDGI | ACDHI | ACEHI
21 | - | - | 550 | 1500 | 2050 | 45543 | 45443 | 45443 | 45543
20 | G,H | 60 | 610 | 1400 | 2010 | 45533 | 45433 | 45433 | 45533
19 | B,C | 80 | 690 | 1300 | 1990 | 44533 | 44433 | 44433 | 44533
18 | B,E | 80 | 770 | 1200 | 1970 | 43533 | 44433 | 44433 | 44433
17 | B,D,E | 120 | 890 | 1100 | 1990 | 42533 | 44333 | 44333 | 44333
×
×
×
×
×