## Exercise 1
Activity code | Activity description | predecessors | Activity code | optimistic | Most likely | Pessimistic | T(e) | variance | [6 empty] | 12 |  | 32
A | Start story draft using template | - | A | 4 | 7 | 10 | 7 | 1 | 0 |  | 7 |  |  |  | 0 | D |  |  |  |  | 32 |  | 38 | 38 |  | 43
B | Research client firm | (SS)A | B | 2 | 4 | 8 | 4.3333 | 1 | 0 | A |  |  |  |  | 12 | 20 | 32 |  |  |  | 0 | H |  | 0 | J
C | Create “due diligence” rough draft | A,B | C | 2 | 5 | 8 | 5 | 1 | 0 | 7 | 7 | 7 |  | 12 | [6 empty] | 32 | 6 | 38 | 38 | 5 | 43
D | Coordinate needs proposal with client | C | D | 16 | 19 | 28 | 20 | 4 |  | SS |  | 0 | C
E | Estimate future demand and cash flows | C | E | 6 | 9 | 24 | 11 | 9 | 0 |  | 4.3333 | 7 | 5 | 12 | 12 |  | 24 |  |  |  | 30 |  | 39 |  |  |  | 43 |  | 72.6667
F | Draft future plans for client company | E | F | 1 | 7 | 13 | 7 | 4 | 2.6667 | B |  |  |  |  | 8 | G |  |  |  |  | 4 | I |  |  |  |  | 0 | K
G | Create and approve legal documents | C | G | 4 | 10 | 28 | 12 | 16 | 2.6667 | 4.3333 | 7 |  |  |  | 20 | 12 | 32 |  |  |  | 34 | 9 | 43 |  |  |  | 43 | 29.6667 | 72.6667
H | Integrate all drafts into first-draft proposal | D, F, G | H | 2 | 5 | 14 | 6 | 4
I | Line up potential sources of capital | G, F | I | 5 | 8 | 17 | 9 | 4
J | Check, approve, and print final legal proposal | H | J | 2 | 5 | 8 | 5 | 1 | [6 empty] | 12 |  | 23 | 23 |  | 30
K | Sign contracts and transfer funds | I, J | K | 17 | 29 | 45 | 29.6667 | 21.7778 | [6 empty] | 2 | E |  | 2 | F
[15 empty] | 14 | 11 | 25 | 25 | 7 | 32
critical activities | T(e) | variance
A | 7 | 1
C | 5 | 1
D | 20 | 4
H | 6 | 4
J | 5 | 1
K | 29.6667 | 21.7778
Expected project duration | 72.6667
project standard deviation | 5.7252
Z | -0.46578
chance of this project | 32.07% | this project does not meet the 95% chance criterion
chance | 95%
Z | 1.6449
Project Average duration must be | 60.5829 | Compressing to 61 days will improve the chance of meeting the 95% confidence level

## Exercise 2
Time in Workdays
# | Task Name | Optimistic Dur. | Most Likely Dur. | Pessimistic Dur. | Immediate Predecessor | Critical Path | T(e) | variance
1 | AET DATA CENTER MIGRATION | 54 | 68 | 92 |  |  |  |  | Expected project duration | 69
2 | Team meeting | 0.5 | 1 | 1.5 |  | ✓ | 1 | 0.027778 | project standard deviation | 2.4152
3 | Hire contractors | 6 | 7 | 8 | 2 |  | 7 | 0.11111
4 | Network design | 12 | 14 | 16 | 2 |  | 14 | 0.44444 | Scheduled duration | 68
5 | Ventilation system | — | — | — | — |  | — | —
6 | Order ventilation system | 18 | 21 | 30 | 2 |  | 22 | 4 | Z | -0.41404
7 | Install ventilation system | 5 | 7 | 9 | 6 |  | 7 | 0.44444 | chance of this project | 33.94%
8 | New racks | — | — | — | — |  | — | —
9 | Order new racks | 13 | 14 | 21 | 2 | ✓ | 15 | 1.7778 | 93 percent chance of completion within 68 days.
10 | Install racks | 17 | 21 | 25 | 9 | ✓ | 21 | 1.7778
11 | Power supplies and cables | — | — | — | — |  |  | — | Probablity | 0.93
12 | Order power supplies & cables | 6 | 7 | 8 | 2 |  | 7 | 0.11111 | Z | 1.4758
13 | Install power supplies | 5 | 5 | 11 | 12, 16 |  | 6 | 1 | Expected project duration | 64.4356
14 | Install cables | 6 | 8 | 10 | 12, 16 | ✓ | 8 | 0.44444
15 | Renovation of data centre | 19 | 20 | 27 | 3, 4 |  | 21 | 1.7778
16 | City inspection | 1 | 2 | 3 | 3, 7, 10 | ✓ | 2 | 0.11111
17 | Switchover Meetings | — | — | — | — |  | — | —
18 | Facilities | 7 | 8 | 9 | 14 |  | 8 | 0.11111
19 | Operations/systems | 5 | 7 | 9 | 14 |  | 7 | 0.44444
20 | Operations/telecommunications | 6 | 7 | 8 | 14 |  | 7 | 0.11111
21 | Systems & applications | 7 | 7 | 13 | 14 | ✓ | 8 | 1
22 | Customer service | 5 | 6 | 13 | 14 |  | 7 | 1.7778
23 | Power check | 0.5 | 1 | 1.5 | 13, 14, 15 |  | 1 | 0.027778
24 | Install test servers | 5 | 7 | 9 | 2, 3, 18, 19, 20, 21 | ✓ | 7 | 0.44444
25 | Management safety check | 1 | 2 | 3 | 7, 23, 24 | ✓ | 2 | 0.11111
26 | Primary systems check | 1.5 | 2 | 2.5 | 25 | ✓ | 2 | 0.027778
27 | Set date for move | 1 | 1 | 1 | 26 | ✓ | 1 | 0
28 | Complete move | 1 | 2 | 3 | 27 | ✓ | 2 | 0.11111